|  |  |  |  |
| --- | --- | --- | --- |
| **University** | **GEORGIANTECHNICAL UNİVERSİTY** | | |
| **Activity** | **Yes** | **No** | **Comments/recommendations** |
| 1. CC: Analisys SWOT of Curricula of the PC HEIs | + |  | Completed |
| 2. CC: Analisys SWOT of Curricula of the EU HEIs |  | n/a |  |
| 3. CC: Development of Double Degrees programmes in Architecture/Urban Planning | + |  | Double Degree Programme was developed on architecture field for Master level |
| 4. CC: Final version of the Joint Degrees (JD) |  | - | GTU is going to sign Double Degree Agreement.  **Recommendation**: Speed up the process of DD Agreement signing. |
| 5. MC: Implementation of newly developed JD into HEIs’ regular Curricula offer |  | - | Implementation of this activity depends on signing by both University |
| 6. MC: EU teachers' mobility to assist the integration of new JD to PC HEIs |  | - |  |
| 7. MC: PC students' mobility to EU for Innovation/Entrepreneurship trainings | +/- |  | Selection process of students in a process. |
| 8. MC: Students' thesis on new Joint Degree: preparation, defence |  | - | This activity should be implemented after student’s mobility |
| 9. CC: Teaching materials for teachers/students: writing, publishing |  | - | Some teaching materials for teachers/students are ready, some of them is needed to be developed |
| 10. MC: e-learning classes for PC students |  | - | Taking into account a local law on purchase of equipment, Tempus Office of Georgia recommended Georgian universities to buy equipment in Europe. |
| 11. CC: Development of Joint Degrees programmes in Environmental Sciences/Climate Engineering |  | - | The situation regarding Double degree programme in the field of Environmental Sciences/Climate Engineering is not clear, because of coordination team at the university was changed and weak connection and cooperation between previous and new coordinators.  **Recommendation**: Connection and cooperation should be strengthened. |
| 12. CC: Final version of the Joint Degrees (JD) |  | - |  |
| 13. MC: Implementation of newly developed JD into HEIs’ regular Curricula offer |  | - |  |
| 14. MC: EU teachers mobility to assist the integration of new JD to PC HEIs |  | - |  |
| 15. MC: PC students mobility to EU for Innovation/Entrepreneurship trainings |  | - |  |
| 16. MC: Students' thesis on new Joint Degree: preparation, defense |  | - |  |
| 17. CC: Teaching materials for teachers/students: writing, publishing |  | - |  |
| 18. MC: e-learning classes for PC students |  | - |  |
| 19. QC: Preparation of QAS Guidelines for the PC HEIs |  | n/a |  |
| 20. MC: Courses of Technical English for PC teachers/students |  | - |  |
| 21. MC: Installation of e-learnig classes and teleconferences' rooms |  | - |  |
| 22. MC: Teaching materials: translation, adaptation at PC HEIs |  | - | Not started |
| 23. MC: PC teachers mobility to EU HEIs for training methods' upgrade | +/- |  | Selection process of teachers in a process. There are good potential between staff. However one problem with this activity was revealed – TSU staff does not agree with Tempus programme requirements on staff mobility payments. Staff of TSU would like to participate in motilities if they travel expenses will be paid before mobility. |
| 24. QC: Inter-universities visits for Quality Control | + |  | My visit to TSU and GTU. |
| 25. QC: Internal monitoring of the action in Partner Countries |  | - |  |
| 26. QC: Internal monitoring of the action in EU Countries |  | n/a |  |
| 27. QC: Internal monitoring visits to PC HEIs |  | - |  |
| 28. QC: Inter-project coaching | + |  | GTU team conducts exchange of expirience in diferent Tempus events organised in country and abroad as well. |
| 29. QC: External Independent evaluation of the project |  | n/a |  |
| 30: QC: Financial audits |  | n/a |  |
| 31. MC: Promotion of the project's activities/results in Partner Countries |  | - | This process will be started after signing the agreement by both universities.  **Recommendation**: Promotion of the project's activities must be started immediately without waiting signing of Agreement |
| 32. MC: Promotion of the project's activities/results in EU Countries |  | n/a |  |
| 33. MC: Project website with Moodle platform: creation, use, support |  | - | **Recommendation:** workshop for using Moodle should be organized between department staff. |
| 34. MC: Supply the repository with scientific/academic/administrative publications |  | - |  |
| 35. MC: Seek for projects/contracts for RETHINK partners in EU Countries |  | - |  |
| 36. MC: Seek for projects/contracts for RETHINK partners in Partner Countries |  | - |  |
| 37. MC: Preparation of Joint Degrees for evaluation/accreditation in Partner Countries |  | - | This process will be started after signing the agreement by both universities. |
| 38. MC: Preparation of Joint Degrees for evaluation/accreditation in EU Countries |  | n/a |  |
| 39. MC: Project's meetings: strategy, publishing of results | + |  | GTU representatives participate in all Coordination meetings of the project. Some results were published on the website of the project. |
| 40. MC: Coordination of the project. | + |  | The Contact Person is always in contact with the RETHINK Coordinator by email, skype and phone. |
| 41. MC: Management of the project by the PC HEIs | +/- |  | Management of the project at the GTU is changed. |
| 42. MC: Management of the project by the EU HEIs | + |  |  |
| 43. MC:Teleconferences for the intermediate strategy control | + |  |  |