|  |  |  |  |
| --- | --- | --- | --- |
| **University** | **TBİLİSİ STATE UNİVERSİTY** | | |
| **Activity** | **Yes** | **No** | **Comments/recommendations** |
| 1. CC: Analisys SWOT of Curricula of the PC HEIs | + |  | Completed and put on the website of the project |
| 2. CC: Analisys SWOT of Curricula of the EU HEIs |  | n/a |  |
| 3. CC: Development of Double Degrees programmes in Architecture/Urban Planning | + |  | Double Degree Programme was developed on urbanism field for PhD level |
| 4. CC: Final version of the Joint Degrees (JD) |  | - | Agreement between universities was signed only by TSU and sent to Lisbon University for signing. **Recommendation** – Inform the Coordinator of the project about delay with signing process and ask to speed up the process. |
| 5. MC: Implementation of newly developed JD into HEIs’ regular Curricula offer |  | - | Implementation of this activity depends on signing the Agreement by Lisbon University. |
| 6. MC: EU teachers' mobility to assist the integration of new JD to PC HEIs |  | - |  |
| 7. MC: PC students' mobility to EU for Innovation/Entrepreneurship trainings |  | - | Selection process of students in a process. There are some potential students on the department. |
| 8. MC: Students' thesis on new Joint Degree: preparation, defence |  | - | This activity will be implemented after student’s mobility |
| 9. CC: Teaching materials for teachers/students: writing, publishing | +/- |  | Some teaching materials for teachers/students are ready, some of them is needed to be developed |
| 10. MC: e-learning classes for PC students |  | - | Taking into local law on purchase of equipment Tempus Office of Georgia recommended Georgian universities to buy equipment in Europe. **Recommendation**: TSU team must address to the Coordinator of the project to start the process of equipment purchasing in Europe. |
| 11. CC: Development of Joint Degrees programmes in Environmental Sciences/Climate Engineering |  | n/a | DD in this field will not be developed |
| 12. CC: Final version of the Joint Degrees (JD) |  | n/a |  |
| 13. MC: Implementation of newly developed JD into HEIs’ regular Curricula offer |  | n/a |  |
| 14. MC: EU teachers mobility to assist the integration of new JD to PC HEIs |  | n/a |  |
| 15. MC: PC students mobility to EU for Innovation/Entrepreneurship trainings |  | n/a |  |
| 16. MC: Students' thesis on new Joint Degree: preparation, defence |  | n/a |  |
| 17. CC: Teaching materials for teachers/students: writing, publishing |  | n/a |  |
| 18. MC: e-learning classes for PC students |  | n/a |  |
| 19. QC: Preparation of QAS Guidelines for the PC HEIs |  | n/a |  |
| 20. MC: Courses of Technical English for PC teachers/students |  | - | Implementation of this activity depends on signing the Agreement by Lisbon University. **Recommendation**: Courses of technical English must be started without waiting signing of Agreement. |
| 21. MC: Installation of e-learning classes and teleconferences' rooms |  | - |  |
| 22. MC: Teaching materials: translation, adaptation at PC HEIs |  | - | Implementation of this activity depends on signing the Agreement by Lisbon University. **Recommendation**: Translation of teaching materials must be started immediately without waiting signing of Agreement. |
| 23. MC: PC teachers mobility to EU HEIs for training methods' upgrade | +/- |  | Selection process of teachers in a process. There are good potential staff. However one problem with this activity was revealed – TSU staff does not agree with Tempus programme requirements on staff mobility payments. Staff of TSU would like to participate in motilities if their travel expenses would be paid before mobility. |
| 24. QC: Inter-universities visits for Quality Control | + |  | My visit to TSU and TTU |
| 25. QC: Internal monitoring of the action in Partner Countries |  | - |  |
| 26. QC: Internal monitoring of the action in EU Countries |  | n/a |  |
| 27. QC: Internal monitoring visits to PC HEIs | +/- |  | Experienced TSU team gives a support and advice to Georgian Technical University team to implement some activities of the project. |
| 28. QC: Inter-project coaching | + |  | TSU has a lot of Tempus projects and team occurs inter-project coaching with other project representatives in different Tempus events. |
| 29. QC: External Independent evaluation of the project |  | n/a |  |
| 30: QC: Financial audits |  | n/a |  |
| 31. MC: Promotion of the project's activities/results in Partner Countries |  | - | Implementation of this activity depends on signing the Agreement by Lisbon University. **Recommendation**: Promotion of the project's activities must be started without waiting signing of Agreement. |
| 32. MC: Promotion of the project's activities/results in EU Countries |  | n/a |  |
| 33. MC: Project website with Moodle platform: creation, use, support |  | +/- | TSU staff/students uses Moodle on own web-recourses, e.g. on TSU website. |
| 34. MC: Supply the repository with scientific/academic/administrative publications |  | - |  |
| 35. MC: Seek for projects/contracts for RETHINK partners in EU Countries |  | - |  |
| 36. MC: Seek for projects/contracts for RETHINK partners in Partner Countries |  | - |  |
| 37. MC: Preparation of Joint Degrees for evaluation/accreditation in Partner Countries | +/- |  | Ready to apply to the Ministry of Education. It will be possible after signing agreement by Lissabon University. |
| 38. MC: Preparation of Joint Degrees for evaluation/accreditation in EU Countries |  | n/a |  |
| 39. MC: Project's meetings: strategy, publishing of results | + |  | TSU representatives participate in all Coordination meetings of the project. Some results were published on the website of the project. |
| 40. MC: Coordination of the project. | + |  | The TSU Contact Person is always in contact with the RETHINK Coordinator by email, skype and phone. |
| 41. MC: Management of the project by the PC HEIs | + |  | The project well coordinated by experienced team leader. |
| 42. MC: Management of the project by the EU HEIs | + |  |  |
| 43. MC:Teleconferences for the intermediate strategy control | + |  |  |